## หน้าแรก
Consult Summary Record
โครงการส่งเสริมให้ผู้ประกอบการได้รับมาตรฐาน ISO/IEC 29110 ปีงบประมาณ 2568
Name of Organization :
Name of Consultant :
ครั้งที่ | กิจกรรมการให้คำปรึกษา | วันที่ที่ดำเนินการ | หมายเหตุ/รายละเอียด
1 | กำหนดแผนในการดำเนินงาน และตรวจ process flow
2 | เลือกโครงการนำร่อง
3 | PM - Work Products
4 | SI - Work Products
5 | PM & SI Work Products
6 | Pre-assessment และสรุปผล

## PilotProject
รายละเอียดโครงการนำร่อง (Pilot project)
1. ชื่อโครงการ (Project Name) | พัฒนาระบบ POS ให้รองรับ E-tax
2. ลักษณะของโครงการ (Project Descrription) | บริษัทมีความต้องการเพิ่มฟังก์ชัน POS ให้รองรับการออกใบกำกับภาษีเต็มรูป ในแบบอิเล็กทรอนิคส์ไฟล์ (E-tax) เพื่อรองรับกลุ่มลูกค้าในปัจจุบันและอนาคตที่ต้องการเปิดการใช้งานการขอออกใบกำกับภาษีเต็มรูปแบบอิเล็กทรอนิคส์ไฟล์ เราจึงได้พัฒนาระบบ POS ให้สามารถเชื่อมต่อกับ API ของผู้ให้บริการ E-tax โปรเจกต์นี้เราได้เลือกผู้ให้บริการ Service เป็นของทาง IES
3. ระยะเวลาเริ่มโครงการ (Starting Date) | 1 มีนาคม 2568
4. ระยะเวลาสิ้นสุดโครงการ (Ending Date) | 30 มิถุนายน 2568
5. รวมระยะเวลา (เดือน) (Total Duration in Months) | 4 เดือน
6. จำนวนบุคลากรในโครงการ (คน) (Number of Staff) | 10
7. เหตุผลในการเลือกเป็นโครงการนำร่อง
(Reasons for choosing as the pilot project) | โปรเจกต์มีขนาดไม่ใหญ่มาก และเป็นโปรเจกต์ภายในบริษัท

## WorkProducts
| ISO/IEC 29110 Work Products | ชื่อเอกสาร | Path
1 | Project Initiation
WP.02 | Agreement | E-TAX_AGR_1.0_14032025 | https://drive.google.com/drive/folders/1bSC6U_xaDJNT7zkcg7zbENZfVCJ8JyLx?usp=sharing
2 | Project Planning
| Work Process Flow | E-TAX_PJP_1.0_14032025 | https://drive.google.com/drive/folders/1rx4Y81GwT2Z0lY56ZoBk8sTTv3lqrxXX?usp=drive_link
| Version Control Strategy | E-TAX_PJP_1.0_14032025 | https://drive.google.com/drive/folders/1rx4Y81GwT2Z0lY56ZoBk8sTTv3lqrxXX?usp=drive_link
WP.10 | Project Plan (Val) | E-TAX_PJP_1.0_14032025 | https://drive.google.com/drive/folders/1rx4Y81GwT2Z0lY56ZoBk8sTTv3lqrxXX?usp=drive_link
WP.22 | Validation Record | E-TAX_ValiD_1.0_Poject Planing | https://drive.google.com/drive/folders/1rx4Y81GwT2Z0lY56ZoBk8sTTv3lqrxXX?usp=drive_link
WP.07 | Meeting Record | E-TAX_MOM(Ex)_1.0_14032025 | https://drive.google.com/drive/folders/1rx4Y81GwT2Z0lY56ZoBk8sTTv3lqrxXX?usp=drive_link
WP.11 | Project Repository | Google Drive | https://drive.google.com/drive/folders/1PEXT2cF3fGKs9BF6QateGNAn0yLrfgqO?usp=drive_link
3 | Software Implementation Initiation
WP.05 | Implementation Environment | E-TAX_ImE_1.0_21032025 | https://drive.google.com/drive/folders/1ExaEM5DCbNv2xsecjXeGFysy7qhlZERJ?usp=drive_link
4 | Software Requirements Analysis
WP.13 | Requirements Specification (Ver , Val) | E-TAX_SRS+SD_2.0_24032025 | https://drive.google.com/drive/folders/1rye9eeEnCdLNp43pNLQmg_8VcZZ6lsa1?usp=drive_link
WP.23 | Verification Record | E-TAX_VeriFi_2.0_Software Requirements+Software Design | https://drive.google.com/drive/folders/1rye9eeEnCdLNp43pNLQmg_8VcZZ6lsa1?usp=drive_link
WP.22 | Validation Record | E-TAX_ValiD_1.0_Software Requirements+Software Design | https://drive.google.com/drive/folders/1rye9eeEnCdLNp43pNLQmg_8VcZZ6lsa1?usp=drive_link
5 | Software Design
WP.16 | Software Design (Ver) | E-TAX_SRS+SD_2.0_24032025 | https://drive.google.com/drive/folders/1rye9eeEnCdLNp43pNLQmg_8VcZZ6lsa1?usp=drive_link
|  | Figma : CCCCC | https://drive.google.com/drive/folders/1rye9eeEnCdLNp43pNLQmg_8VcZZ6lsa1?usp=drive_link
WP.23 | Verification Record | E-TAX_VeriFi_2.0_Software Requirements+Software Design | https://drive.google.com/drive/folders/1rye9eeEnCdLNp43pNLQmg_8VcZZ6lsa1?usp=drive_link
6 | Software Construction
WP.15 | Software Components | ไม่มีเอกสาร | https://github.com/vTecApp/api-core-or-phase2/tree/main/src/VerticalTec.Api
WP.14 | Software | ไม่มีเอกสาร | https://github.com/vTecApp/api-core-or-phase2/tree/main/src/VerticalTec.Api
7 | Project Execution, Assessment and Control
WP.04 | Correction Register | E-TAX_CoR_2.0_23052025 | https://drive.google.com/drive/folders/12QY6m_hjvS9sXB_uBNCleLGO4KMeWi5_?usp=drive_link
WP.07 | Meeting Record | External : E-TAX_MOM(Ex)_1.0_14032025 E-TAX_MOM(Ex)_2.0_21032025 E-TAX_MOM(Ex)_3.0_28032025 E-TAX_MOM(Ex)_4.0_09052025 E-TAX_MOM(Ex)_5.0_23052025 E-TAX_MOM(Ex)_6.0_26062025 | https://drive.google.com/drive/folders/12QY6m_hjvS9sXB_uBNCleLGO4KMeWi5_?usp=drive_link
|  | Internal : E-TAX_MOM(In)_1.0_17032025 E-TAX_MOM(In)_2.0_09042025 E-TAX_MOM(In)_3.0_25042025 E-TAX_MOM(In)_4.0_06062025 | https://drive.google.com/drive/folders/12QY6m_hjvS9sXB_uBNCleLGO4KMeWi5_?usp=drive_link
WP.09 | Progress Status Record | External : E-TAX_PSR(Ex)_1.0_14032025 E-TAX_PSR(Ex)_2.0_21032025 E-TAX_PSR(Ex)_3.0_28032025 E-TAX_PSR(Ex)_4.0_09052025 E-TAX_PSR(Ex)_5.0_23052025 E-TAX_PSR(Ex)_6.0_26062025 | https://drive.google.com/drive/folders/12QY6m_hjvS9sXB_uBNCleLGO4KMeWi5_?usp=drive_link
|  | Internal : E-TAX_PSR(In)_1.0_17032025 E-TAX_PSR(In)_2.0_09042025 E-TAX_PSR(In)_3.0_25042025 E-TAX_PSR(In)_4.0_06062025 | https://drive.google.com/drive/folders/12QY6m_hjvS9sXB_uBNCleLGO4KMeWi5_?usp=drive_link
WP.12 | Project Repository Backup | Google Drive(Info Account)
7 | Traceability Control
WP.21 | Traceability Record | E-TAX_TraR_2.0_23052025 | https://drive.google.com/drive/folders/1u4cJ6j_ShH-KhzJw77hA1danfxzYQPYK?usp=drive_link
8 | Software Testing
WP.19 | Test Cases and Test Procedures (Ver) | Unit test cases : E-TAX_TC_2.0_23052025 | https://drive.google.com/drive/folders/1xDnb3G99HJQOzVH1xn-ScMrH_he-WBgz?usp=drive_link
|  | Integration test cases : E-TAX_UAT_2.0_23052025 | https://drive.google.com/drive/folders/1xDnb3G99HJQOzVH1xn-ScMrH_he-WBgz?usp=drive_link
WP.23 | Verification Record (Integration test cases) | E-TAX_VeriFi_1.0_Test Case | https://drive.google.com/drive/folders/1xDnb3G99HJQOzVH1xn-ScMrH_he-WBgz?usp=drive_link
WP.20 | Test Report | E-TAX_TR(TC)_2.0_23052025 E-TAX_TR(UAT)_2.0_23052025 | https://drive.google.com/drive/folders/1xDnb3G99HJQOzVH1xn-ScMrH_he-WBgz?usp=drive_link
| Validation Record (UAT - Customer) | E-TAX_ValiD_1.0_UAT | https://drive.google.com/drive/folders/1xDnb3G99HJQOzVH1xn-ScMrH_he-WBgz?usp=drive_link
9 | Change Management
WP.03 | Change Request | E-TAX_CR_1.0_09042025 | https://drive.google.com/drive/folders/1xDnb3G99HJQOzVH1xn-ScMrH_he-WBgz?usp=drive_link
11 | Software Product Assembly
WP.18 | Software User Documentation (Ver) | E-TAX_SUD_1.0_06052025 | https://drive.google.com/drive/folders/1xDnb3G99HJQOzVH1xn-ScMrH_he-WBgz?usp=drive_link
WP.23 | Verification Record | E-TAX_VeriFi_1.0_Software User Documentation | https://drive.google.com/drive/folders/1xDnb3G99HJQOzVH1xn-ScMrH_he-WBgz?usp=drive_link
WP.08 | Product Operation Guideline (Ver) | E-TAX_POG_1.0_26052025 | https://drive.google.com/drive/folders/1xDnb3G99HJQOzVH1xn-ScMrH_he-WBgz?usp=drive_link
WP.23 | Verification Record | E-TAX_VeriFi_1.0_Product Operation Guideline | https://drive.google.com/drive/folders/1xDnb3G99HJQOzVH1xn-ScMrH_he-WBgz?usp=drive_link
WP.06 | Maintenance Documentation (Ver) | E-TAX_MD_1.0_26052025 | https://drive.google.com/drive/folders/1xDnb3G99HJQOzVH1xn-ScMrH_he-WBgz?usp=drive_link
WP.23 | Verification Record | E-TAX_VeriFi_1.0_Maintenance Documentation | https://drive.google.com/drive/folders/1xDnb3G99HJQOzVH1xn-ScMrH_he-WBgz?usp=drive_link
WP.17 | Software Product (Delivered) | E-TAX_SW(Delivered)_1.0_30062025 | https://drive.google.com/drive/folders/1xDnb3G99HJQOzVH1xn-ScMrH_he-WBgz?usp=drive_link
12 | Project Closure
WP.01 | Acceptance Record | E-TAX_LOA_1.0_28032025 E-TAX_LOA_2.0_30062025 | https://drive.google.com/drive/folders/1xDnb3G99HJQOzVH1xn-ScMrH_he-WBgz?usp=drive_link

## Pre-assessment
Pre-assesssment Result
สำหรับคะแนน : ถ้ามีครบแบบสมบูรณ์ ให้ 1 ¦¦ ถ้ามีค่อนข้างมาก และไม่สมบูรณ์ให้ 0.7 ¦¦ ถ้ามีค่อนข้างน้อย และไม่สมบูรณ์ ให้ 0.3 ¦¦ ถ้าไม่มี ให้ 0
คะแนน
Project Initiation and Planning
1 | Has baslined agreement | 1
2 | Perform cost, technical and schedule feasibility | 1
3 | Select development life cycle | 1
4 | Estimate schedule, effort, cost and duration of work | 1
5 | Create project schedule with human resource allocation | 1
6 | Define deliverable Items and delivery instructions | 1
7 | Identify risks | 1
8 | Identify version control strategy and backup and recovery mechanisms | 1
9 | Validate the project plan and obtain approval from the customer | 1
Project Plan Execution
1 | Monitor the project plan execution | 1
2 | Meetings are recorded (Internal & External) | 1
3 | Implement version control strategy to create baselines as defined | 1
4 | Implement back up and recovery as defined | 1
Project Assessment and Control
1 | Hold regular progress meetings | 1
2 | Record progress status (Plan vs. Actual) | 1
3 | Evaluate and approve change request according to cost, schedule and technical impact | 1
4 | Correction Register (document and track the action to closure) | 1
5 | Risks control (document and track the action to closure) | 1
Project Closure
1 | Acceptance Record (Signed / Approved) | 1
2 | Deliverable Items in Acceptance Records | 1
3 | Store the acceptant record in the Project Repository | 1
4 | Software Product | 1
Software Implementation Initiation & Requirements Analysis
1 | Implementation Environment | 1
2 | Software Requirements Specification | 1
3 | Analyse requirements for correctness and testability | 1
4 | Requirements are communicated | 1
5 | Traceability of requirements in software requirements specification to requirements in agreement | 1
6 | Verify and obtain approval of the Software Requirements Specification | 1
7 | Validate and obtain approval of the Software Requirements Specification | 1
9 | Requirements Baselined (Control the baseline of software product item) | 1
Software Architectural and Detailed Design
1 | Software Architectural Design | 1
2 | Detailed Design | 1
3 | External Interfaces | 1
4 | Internal Interfaces | 1
5 | Traceability of design elements to requirements specification | 1
6 | Verify and obtain approval of softwarearchitectural and detailed design | 1
7 | Design Baselined (Control the baseline of software product item) | 1
Software Construction and Test
1 | Software Components | 1
2 | Unit Test | 1
3 | Software | 1
4 | Test Cases and Test Procedures | 1
5 | Verify and obtain approval of the Test Cases and Test Procedures | 1
6 | Integration Test | 1
7 | Test Report | 1
8 | Traceability of components, test cases and test results to requirements | 1
9 | Test Cases and Test Procedures Baselined (Control the baseline of software product item) | 1
10 | Software component baselined (Control the baseline of software product item) | 1
Software Product Assembly
1 | Software User Document (if applicable) | 1
2 | Product Operation Guideline (if applicable) | 1
3 | Maintenance documentation | 1
4 | Identify all work products to be assembled as baselined software product for delivery | 1
Software Configuration and QA
1 | Project repository for all work product (with versioning and baselines) | 1
2 | Traceability records | 1
3 | Verification records for all verify actions | 1
4 | Validation records for all validate actions | 1

## สรุปผล
กราฟแสดงผลการวัด Pre-assessment
| กระบวนการ | จำนวนคะแนนรวม (เต็ม 55) | ร้อยละที่ได้ในแต่ละกระบวนการ
1 | Project Initiation and Planning | 9 | 100
2 | Project Plan Execution | 4 | 100
3 | Project Assessment and Control | 5 | 100
4 | Project Closure | 4 | 100
5 | Software Implementation Initiation & Requirements Analysis | 8 | 100
6 | Software Architectural and Detailed Design | 7 | 100
7 | Software Construction and Test | 10 | 100
8 | Software Product Assembly | 4 | 100
9 | Software Configuration and QA | 4 | 100
รวมทั้งสิ้น จำนวน |  | 55 | 100